## Pending
# | Job # | Job Name | Contractor | PM | Contact | Phone | Storm | San | Total | Received | Days Pending | Notes | Message-Id
1 | TBD (see PDF) | Saddlestone Phase 2B2D (Add-ons) | Gator | Ian Zanetta | Panfilo Velasco | (941) 915-1497 | See Notes | See Notes | See Notes | 2026-07-15 | 1 | RTP Package (2 of 6). Subject prefix '7 - ST Prod. Pkg (2 of 6)'. Body confirms RTP. Attached PDF: 250052_Saddlestone2B2D_QPS_PO-14.pdf. | <PH0PR02MB7655AC980C97A4B833B016F6E9F82@PH0PR02MB7655.namprd02.prod.outlook.com>
2 | 26-1130 | Audubon Country Club | Jensen Underground Utilities | Ian Zanetta | Kelly Edwards | See email | See Notes | See Notes | See Notes | 2026-07-14 | 2 | RTP package. Kelly Edwards, Estimator / PM, Jensen Underground Utilities, 5585 Taylor Rd, Naples FL 34109. Structure counts in PDF. | <SA2PR02MB76580A11ED1E3ED27A68EE0BE9F92@SA2PR02MB7658.namprd02.prod.outlook.com>
3 | 26-379 | Schandler Hall | Bartolone Excavating | Ian Zanetta | Brandy Bartolone | 239-253-4198 | See Notes | See Notes | See Notes | 2026-07-14 | 2 | RTP Package (2 Strs). Bartolone Excavating, 2188 J & C Blvd, Naples FL 34109. Storm/San split in PDF. | <SA2PR02MB76583236649CC0BAE45EC517E9F92@SA2PR02MB7658.namprd02.prod.outlook.com>
4 | TBD (see PDF) | Wynn Parcel | Jensen Underground Utilities | Ian Zanetta | Lolo Popoca | 239-597-0060 office / 352-601-7544 cell | See Notes | See Notes | See Notes | 2025-08-18 | 332 | OLDEST PENDING (~11 months). Subject has no job # — sent 08-15-25. Estimator/PM at Jensen. GC target was Sept 8; may push to November. Confirm still active. | <PH0PR02MB7655780FF9B7F74E0DA12D84E934A@PH0PR02MB7655.namprd02.prod.outlook.com>
5 | 26-1090 | Daniels Creek Offsite Improvements | Backbay | Keaton Elliott | Tyler Derench | 239-226-1310 | See Notes | See Notes | See Notes | 2026-07-15 | 1 | RTP package. Attachment: 2 -26-1090 - RTP - Daniels Creek Offsite Improvements - Backbay - 7-15-26.pdf. Also included signed Quality Precast - Creekside quote and NTO Info Sheet. | <DS2PR02MB1123410000C37DA5CFB86E45CCAF82@DS2PR02MB11234.namprd02.prod.outlook.com>
6 | 25-952 | Vivid Shores Amenity Center (Storm) | Jensen (per subject) — see notes | Keaton Elliott | Robert D Meadows (per body) | 239-633-3014 | See Notes | See Notes | See Notes | 2026-07-15 | 1 | FLAG: Subject says 25-952 Vivid Shores / Jensen but body lists Robert D Meadows / Stark Sullen Grading and the attached RTP PDF is '6 - 26-840 RTP package - Woodfield - Offsite - Coconut Rd - 7-15-26.pdf'. Included per Rule 8 (subject matches release pattern) but flagged for Keaton confirmation — likely a wrong-job attachment. | <DS2PR02MB1123425476C3B1A3F60C0AF96CAF82@DS2PR02MB11234.namprd02.prod.outlook.com>
7 | 26-221 | West Port Village | Stark Sullen | Keaton Elliott | Chris Barrett, P.E. | 239-284-8157 | See Notes | See Notes | See Notes | 2026-07-14 | 2 | RTP ST (single structure). Address 9890 Bayshore Rd, N. Fort Myers FL 33917. | <DS2PR02MB11234704400CD02163042CC6ECAF92@DS2PR02MB11234.namprd02.prod.outlook.com>
8 | 25-1594 | Dunkin Donuts 951 | BCU | Keaton Elliott | Shannon Lee | 239-466-3980 office / 954-839-7707 cell | See Notes | See Notes | See Notes | 2026-07-14 | 2 | RTP package. BCU Assistant PM. | <DS2PR02MB11234629277733137A160342DCAF92@DS2PR02MB11234.namprd02.prod.outlook.com>
9 | 26-181 | Roadies at Vintage Commerce Center | BCU | Keaton Elliott | Shannon Lee | 239-466-3980 office / 954-839-7707 cell | See Notes | See Notes | See Notes | 2026-07-14 | 2 | RTP package. BCU Assistant PM. | <DS2PR02MB1123453BDE950DAD44586C14BCAF92@DS2PR02MB11234.namprd02.prod.outlook.com>
10 | 26-177 | T-1813 FDOT US-41 Sarasota (FIN# 444612-1-52-01) | C-Squared | Rodrigo Gracia | Sean D'Agostino / Amanda Kelly | 941-345-3093 / 941-720-9236 | See Notes | See Notes | See Notes | 2026-06-17 | 29 | RELEASED to Prod. Contractor targeting September start. seand@c-squaredcgc.com / amandak@c-squaredcgc.com. | <CY4PR02MB3174D931B4B811DDDCCA09DC8BE42@CY4PR02MB3174.namprd02.prod.outlook.com>
11 | 25-1671 | T-1922 FDOT Cortez Rd (FIN# 445044-1-52-01 & 445044-1-52-03) | Sun Civil | Rodrigo Gracia | Brian Brooks | 352-346-1852 | See Notes | See Notes | See Notes | 2026-06-17 | 29 | RELEASED to Prod. (22 Strs). Contractor targeting end of September. bbrooks@sun-civil.com. | <CY4PR02MB31742D292E0AFA6C112303E08BE42@CY4PR02MB3174.namprd02.prod.outlook.com>

## Flagged
Reason | Job # | Job Name | Contractor | PM | Detail | Received (RE:)
Subject/body/attachment mismatch — job # 25-952 in subject but customer & PDF are different job | 25-952 | Vivid Shores Amenity Center (Storm) vs Woodfield Coconut Rd (attached) | Subject: Jensen; Body: Stark Sullen; Attachment: Woodfield | Keaton Elliott | Subject: '(4 - 25-952 - RTP - Storm - Vivid Shores Amenity Center - Jensen 6-23-26)'. Body customer info: Robert D Meadows, Stark Sullen Grading, 9890 Bayshore Rd, N. Ft Myers, 239-633-3014. Attached RTP PDF is '6 - 26-840 RTP package - Woodfield - Offsite - Coconut Rd - 7-15-26.pdf' plus 'QPS Quote - Woodfield - Offsite - Coconut Rd - 5-18-26 -SIGNED.pdf'. Included in pending per Rule 8 (subject matches release pattern). Keaton to confirm which job is actually being released — likely a wrong-attachment mistake. | 2026-07-15
RE: thread only in inbox — original bare RTP filed. Carryover from 2026-07-15 flag (still unresolved). | 26-521 | Tuttle Ave | Woodruff | Maryanne Siurano | Original 'RTP - 26-521 - Tuttle Ave - Woodruff' (7/9/26) is not in inbox. Only RE: follow-ups remain (revised S-502 dwg 7/13; PO received 7/14). Per Rule 8, excluded from pending. Yesterday's flag not addressed. If Ryan considers this still pending, unfile the parent so it recirculates as a real RTP. | 2026-07-14